## Summary
Cost report: Office Renovation
Generated 26 Oct 2026 07:15 UTC
Total estimated | 2085000
Total actual | 2222500
Variance | 137500
% Variance | 6.59
Status | Over budget
Items | 10
AI summary
1. Overall position: Office Renovation is over budget by 137,500.00 (+6.6%). Actual spend is 2,222,500.00 against an estimate of 2,085,000.00 across 10 items. 2. Key drivers: - Hardware: +58,000.00 (+4.7%) - IT Services: +48,000.00 (+50.5%) - General: +36,000.00 (+144.0%) 3. Unusual expenses: - Network setup (High): +50.5% over estimate (threshold 25%) - Miscellaneous supplies (High): +144.0% over estimate (threshold 25%) 4. Recommendations: - Review invoices and scope for Network setup, Miscellaneous supplies. - Savings in Software could partly offset overruns. - Add a contingency buffer to future estimates for categories that ran over.
Source: rule-based (no GROQ_API_KEY set)

## Items
Item | Category | Estimated | Actual | Variance | % Variance | Status
Laptops (10 units) | Hardware | 850000 | 912000 | 62000 | 7.29 | Over budget
Office chairs | Furniture | 120000 | 118500 | -1500 | -1.25 | On budget
Network setup | IT Services | 95000 | 143000 | 48000 | 50.53 | Over budget
Software licenses | Software | 210000 | 205000 | -5000 | -2.38 | Under budget
Electrical rewiring | Construction | 180000 | 176000 | -4000 | -2.22 | Under budget
Painting | Construction | 65000 | 71000 | 6000 | 9.23 | Over budget
Air conditioners | Hardware | 300000 | 298000 | -2000 | -0.67 | On budget
Project manager fee | Labour | 150000 | 150000 | 0 | 0 | On budget
Security cameras | Hardware | 90000 | 88000 | -2000 | -2.22 | Under budget
Miscellaneous supplies | General | 25000 | 61000 | 36000 | 144 | Over budget

## Categories
Category | Items | Estimated | Actual | Variance | % Variance | Status
Hardware | 3 | 1240000 | 1298000 | 58000 | 4.68 | Over budget
IT Services | 1 | 95000 | 143000 | 48000 | 50.53 | Over budget
General | 1 | 25000 | 61000 | 36000 | 144 | Over budget
Construction | 2 | 245000 | 247000 | 2000 | 0.82 | On budget
Labour | 1 | 150000 | 150000 | 0 | 0 | On budget
Furniture | 1 | 120000 | 118500 | -1500 | -1.25 | On budget
Software | 1 | 210000 | 205000 | -5000 | -2.38 | Under budget

## Unusual expenses
Item | Category | Variance | % Variance | Severity | Reasons
Network setup | IT Services | 48000 | 50.53 | High | '+50.5% over estimate (threshold 25%); % variance is a statistical outlier (above +24.8%)
Miscellaneous supplies | General | 36000 | 144 | High | '+144.0% over estimate (threshold 25%); % variance is a statistical outlier (above +24.8%)